## Tabelle1
Milestone | Description | Planned | Achieved
First Global Meeting | Introduction session with Team Kenya to get to know each other and sharing our requirements and expectations of the project | 2013-10-01 | 2013-10-01
Final definition of Requirements and Roles | Get all requirements together and splitting up the project tasks | 2013-10-31 | 2013-12-03
Finishing Prototype | A complete Prototype of the product | 2013-12-01 | 2013-12-15
Report | A complete final report of the project | 2013-12-13 | 2013-12-16